## Project Profitability
Job Costing & Project Profitability Calculator
Quoted vs. actual margin · cost variance · hours overrun · realization rate · effective hourly rate · made by sheetflow.cloud
PROJECT FINANCIALS |  |  | COST BREAKDOWN
Project Revenue | 25000 | what the client paid | Actual Labor Cost | 13125
Quoted Project Cost | 15000 | original cost estimate | Total Overhead Cost | 1968.75
Target Gross Margin Percent | 50 | your firm's standard target | Total Direct Cost | 17093.75
LABOR |  |  | PROFITABILITY
Loaded Hourly Rate | 75 | blended loaded rate across team | Quoted Gross Margin Percent | 40 | % at original quote
Quoted Hours | 150 | hours in original scope | Gross Margin Percent | 31.625 | % at actual cost
Actual Hours Logged | 175 | all hours worked incl. non-billable
Billable Hours | 155 | hours invoiced to client
DIRECT COSTS & OVERHEAD |  |  | VARIANCE ANALYSIS
Subcontractor & Freelancer Cost | 1500 | external labor for this project | Cost Variance | 2093.75 | + = over budget
Direct Project Expenses | 500 | software, travel, materials | Margin Variance (Percentage Points) | 8.375 | pp erosion from quote
Overhead Rate Percent | 15 | % of direct labor — firm allocation | Hours Variance | 25 | + = over scope
|  |  | GROSS PROFIT | 7906.25
EFFICIENCY & BENCHMARK
|  |  | Realization Rate | 88.5714 | % of hours billed
|  |  | Effective Hourly Rate | 161.2903 | revenue ÷ billed hours
|  |  | Cost Per Hour Delivered | 97.6786 | cost ÷ actual hours
|  |  | Margin vs. Target | -18.375 | pp vs. target (– = below)